## Overview
| Minty Game Engine | Time Worked
Total Hours Worked: | 1059.25 | 44 days | 3 hours | 15 minutes
Hours Worked Today: | 4
Total Calendar Days Worked: | 247
Longest Streak: | 17
Current Streak: | 1

## Data
Name | Start Date | Start Time | End Date | End Time | Start Date Value | End Date Value | Elapsed Hours Raw | Streak | Elapsed Hours | Notes
Mitch | 2023-09-14 | 12:00 | 2023-09-14 | 20:45 | 45183 | 45183 | 8.75 | 1 | 8.75 | Started work on building and running games through the engine.
Mitch | 2023-09-14 | 21:30 | 2023-09-15 | 1:15 | 45183 | 45184 | 3.75 | 1 | 3.75 | Finished debugging and building in engine.
Mitch | 2023-09-15 | 12:00 | 2023-09-15 | 13:00 | 45184 | 45184 | 1 | 2 | 1 | Worked on splitting up the render engine. Made window class.
Mitch | 2023-09-15 | 13:15 | 2023-09-15 | 17:00 | 45184 | 45184 | 3.75 | 2 | 3.75 | Fixed release building. ABSOLUTE HEADACHE.
Mitch | 2023-09-15 | 20:00 | 2023-09-15 | 21:00 | 45184 | 45184 | 1 | 2 | 1 | Bug fixes.
Mitch | 2023-09-15 | 21:30 | 2023-09-16 | 0:30 | 45184 | 45185 | 3 | 2 | 3 | Started importing old engine files.
Mitch | 2023-09-16 | 11:20 | 2023-09-16 | 18:00 | 45185 | 45185 | 6.6667 | 3 | 6.6667 | Started importing minty, worked on meshes and rendering.
Mitch | 2023-09-16 | 19:00 | 2023-09-17 | 1:20 | 45185 | 45186 | 6.3333 | 3 | 6.3333 | Input system, started work on materials.
Mitch | 2023-09-17 | 9:15 | 2023-09-17 | 11:15 | 45186 | 45186 | 2 | 4 | 2 | Viewport, background color, worked on materials
Mitch | 2023-09-17 | 14:45 | 2023-09-17 | 17:00 | 45186 | 45186 | 2.25 | 4 | 2.25 | Trying to figure out descriptor sets
Mitch | 2023-09-17 | 19:00 | 2023-09-17 | 21:45 | 45186 | 45186 | 2.75 | 4 | 2.75 | Still trying.
Mitch | 2023-09-17 | 23:20 | 2023-09-18 | 0:45 | 45186 | 45187 | 1.4167 | 4 | 1.4167 | Worked on materials, allowing for multiple materials, STILL working on understanding descriptor sets.
Mitch | 2023-09-18 | 12:00 | 2023-09-18 | 13:00 | 45187 | 45187 | 1 | 5 | 1 | Got materials kind of working, they throw lots of errors.
Mitch | 2023-09-18 | 16:30 | 2023-09-18 | 16:45 | 45187 | 45187 | 0.25 | 5 | 0.25 | Worked on properly setting descriptor sets.
Mitch | 2023-09-19 | 7:45 | 2023-09-19 | 13:45 | 45188 | 45188 | 6 | 6 | 6 | Materials, shaders and textures all stored in renderer. Worked on fixing descriptors.
Mitch | 2023-09-19 | 15:50 | 2023-09-19 | 17:25 | 45188 | 45188 | 1.5833 | 6 | 1.5833 | Kept working on fixing descriptors. Got it running again.
Mitch | 2023-09-19 | 20:55 | 2023-09-20 | 1:40 | 45188 | 45189 | 4.75 | 6 | 4.75 | Updated excel sheet, got the initial material system working.
Mitch | 2023-09-20 | 13:35 | 2023-09-20 | 16:00 | 45189 | 45189 | 2.4167 | 7 | 2.4167 | Attempted to make a dynamic texture array, it didn't work.
Mitch | 2023-09-20 | 17:35 | 2023-09-20 | 18:00 | 45189 | 45189 | 0.41667 | 7 | 0.41667 | Vulkan error names.
Mitch | 2023-09-20 | 19:45 | 2023-09-20 | 21:00 | 45189 | 45189 | 1.25 | 7 | 1.25 | Refactoring and documentation.
Mitch | 2023-09-21 | 13:00 | 2023-09-21 | 21:30 | 45190 | 45190 | 8.5 | 8 | 8.5 | Serialization, scene parsing, started separating "game" code from engine.
Mitch | 2023-09-21 | 23:50 | 2023-09-22 | 0:50 | 45190 | 45191 | 1 | 8 | 1 | Moved texture, shader, material creation into project. Fixed Runtime args.
Mitch | 2023-09-22 | 12:00 | 2023-09-22 | 12:50 | 45191 | 45191 | 0.83333 | 9 | 0.83333 | Started refactoring all function names.
Mitch | 2023-09-22 | 13:20 | 2023-09-22 | 17:15 | 45191 | 45191 | 3.9167 | 9 | 3.9167 | Finished refactoring, worked on scenes.
Mitch | 2023-09-23 | 9:30 | 2023-09-23 | 13:45 | 45192 | 45192 | 4.25 | 10 | 4.25 | Scene loading, SceneManager, registering Systems and Components for loading. Good progress.
Mitch | 2023-09-23 | 15:40 | 2023-09-23 | 19:30 | 45192 | 45192 | 3.8333 | 10 | 3.8333 | More scene integration.
Mitch | 2023-09-24 | 16:10 | 2023-09-24 | 17:55 | 45193 | 45193 | 1.75 | 11 | 1.75 | Worked on fixing EnTT issues.
Mitch | 2023-09-24 | 19:30 | 2023-09-24 | 22:45 | 45193 | 45193 | 3.25 | 11 | 3.25 | Debugging why entt::registry.create() won't work.
Mitch | 2023-09-25 | 14:00 | 2023-09-25 | 16:15 | 45194 | 45194 | 2.25 | 12 | 2.25 | Fixed scene move constructor crap. Scenes working.
Mitch | 2023-09-25 | 19:45 | 2023-09-25 | 21:45 | 45194 | 45194 | 2 | 12 | 2 | Worked on loading a scene from a file and other small helper functions with the registry classes.
Mitch | 2023-09-25 | 22:40 | 2023-09-26 | 0:15 | 45194 | 45195 | 1.5833 | 12 | 1.5833 | Worked on scene serialization/deserialization.
Mitch | 2023-09-26 | 10:55 | 2023-09-26 | 13:40 | 45195 | 45195 | 2.75 | 13 | 2.75 | Finished scene (de)serialization.
Mitch | 2023-09-26 | 14:15 | 2023-09-26 | 15:45 | 45195 | 45195 | 1.5 | 13 | 1.5 | Worked on merging RenderSystem into Renderer.
Mitch | 2023-09-26 | 16:00 | 2023-09-26 | 16:30 | 45195 | 45195 | 0.5 | 13 | 0.5 | Refactoring.
Mitch | 2023-09-26 | 21:00 | 2023-09-26 | 22:15 | 45195 | 45195 | 1.25 | 13 | 1.25 | Finish multiple entity rendering.
Mitch | 2023-09-27 | 20:30 | 2023-09-27 | 21:00 | 45196 | 45196 | 0.5 | 14 | 0.5 | Refactoring.
Mitch | 2023-09-27 | 23:00 | 2023-09-28 | 1:45 | 45196 | 45197 | 2.75 | 14 | 2.75 | Multiple entitiy rendering tests.
Mitch | 2023-09-28 | 15:30 | 2023-09-28 | 16:45 | 45197 | 45197 | 1.25 | 15 | 1.25 | Started on ImGui.
Mitch | 2023-09-28 | 18:00 | 2023-09-28 | 19:40 | 45197 | 45197 | 1.6667 | 15 | 1.6667 | Working on ImGui.
Mitch | 2023-09-28 | 22:00 | 2023-09-29 | 0:00 | 45197 | 45198 | 2 | 15 | 2 | Worked on GUI console.
Mitch | 2023-09-30 | 14:30 | 2023-09-30 | 15:50 | 45199 | 45199 | 1.3333 | 1 | 1.3333 | Multitheading for console.
Mitch | 2023-09-30 | 15:30 | 2023-09-30 | 18:00 | 45199 | 45199 | 2.5 | 1 | 2.5 | Console implemented in editor.
Mitch | 2023-09-30 | 20:00 | 2023-09-30 | 22:15 | 45199 | 45199 | 2.25 | 1 | 2.25 | Started work on viewport in editor.
Mitch | 2023-10-02 | 12:00 | 2023-10-02 | 13:00 | 45201 | 45201 | 1 | 1 | 1 | Worked on viewport.
Mitch | 2023-10-02 | 14:00 | 2023-10-02 | 17:00 | 45201 | 45201 | 3 | 1 | 3 | Worked on viewport.
Mitch | 2023-10-02 | 18:40 | 2023-10-02 | 22:35 | 45201 | 45201 | 3.9167 | 1 | 3.9167 | Worked on refactoring Renderer, added RendererBuilder, started masking Vulkan.
Mitch | 2023-10-03 | 10:30 | 2023-10-03 | 13:45 | 45202 | 45202 | 3.25 | 2 | 3.25 | Worked on ShaderBuilder, decided to not mask Vulkan.
Mitch | 2023-10-03 | 14:10 | 2023-10-03 | 15:00 | 45202 | 45202 | 0.83333 | 2 | 0.83333 | Worked on builders.
Mitch | 2023-10-03 | 17:30 | 2023-10-03 | 18:30 | 45202 | 45202 | 1 | 2 | 1 | Worked on builders.
Mitch | 2023-10-03 | 19:10 | 2023-10-03 | 21:00 | 45202 | 45202 | 1.8333 | 2 | 1.8333 | Worked on builders.
Mitch | 2023-10-03 | 21:30 | 2023-10-03 | 23:00 | 45202 | 45202 | 1.5 | 2 | 1.5 | Worked on builders.
Mitch | 2023-10-04 | 12:00 | 2023-10-04 | 12:50 | 45203 | 45203 | 0.83333 | 3 | 0.83333 | Worked on builders.
Mitch | 2023-10-04 | 14:30 | 2023-10-04 | 17:30 | 45203 | 45203 | 3 | 3 | 3 | Worked on builders, refactored Renderer.
Mitch | 2023-10-04 | 18:30 | 2023-10-04 | 21:30 | 45203 | 45203 | 3 | 3 | 3 | Starting to wrap up builders.
Mitch | 2023-10-05 | 10:30 | 2023-10-05 | 12:30 | 45204 | 45204 | 2 | 4 | 2 | Got build working.
Mitch | 2023-10-05 | 13:45 | 2023-10-05 | 15:00 | 45204 | 45204 | 1.25 | 4 | 1.25 | Started moving shader-specific code to the project from the engine.
Mitch | 2023-10-05 | 15:40 | 2023-10-05 | 17:00 | 45204 | 45204 | 1.3333 | 4 | 1.3333 | Refactor Mesh to account for new builder system.
Mitch | 2023-10-05 | 19:30 | 2023-10-05 | 20:30 | 45204 | 45204 | 1 | 4 | 1 | Work on Material building.
Mitch | 2023-10-06 | 11:00 | 2023-10-06 | 21:30 | 45205 | 45205 | 10.5 | 5 | 10.5 | Got debugging working in VS Code, worked on getting project to run finally.
Mitch | 2023-10-10 | 13:00 | 2023-10-10 | 15:45 | 45209 | 45209 | 2.75 | 1 | 2.75 | Debugging null descriptors.
Mitch | 2023-10-12 | 10:30 | 2023-10-12 | 17:30 | 45211 | 45211 | 7 | 1 | 7 | Got the program running again. Started working on fixing the shaders.
Mitch | 2023-10-13 | 15:00 | 2023-10-13 | 17:00 | 45212 | 45212 | 2 | 2 | 2 | Worked on fixing shaders and rendering.
Mitch | 2023-10-15 | 19:30 | 2023-10-15 | 21:00 | 45214 | 45214 | 1.5 | 1 | 1.5 | Worked on fixing shaders and rendering.
Mitch | 2023-10-16 | 13:00 | 2023-10-16 | 17:00 | 45215 | 45215 | 4 | 2 | 4 | Fixed the horrendous named variable bug.
Mitch | 2023-10-16 | 20:00 | 2023-10-16 | 23:00 | 45215 | 45215 | 3 | 2 | 3 | Almost fixed multi-material rendering, again.
Mitch | 2023-10-17 | 10:00 | 2023-10-17 | 16:30 | 45216 | 45216 | 6.5 | 3 | 6.5 | Fixed rendering, added transforms.
Mitch | 2023-10-17 | 21:00 | 2023-10-18 | 0:40 | 45216 | 45217 | 3.6667 | 3 | 3.6667 | Added Quaternions, worked on fixing transform/rotation problems.
Mitch | 2023-10-18 | 12:00 | 2023-10-18 | 12:45 | 45217 | 45217 | 0.75 | 4 | 0.75 | Worked on fixing rendering issues.
Mitch | 2023-10-18 | 15:30 | 2023-10-18 | 18:10 | 45217 | 45217 | 2.6667 | 4 | 2.6667 | Fixed rendering issues, decided to make +Y down. Started on to_string() for all types.
Mitch | 2023-10-18 | 20:00 | 2023-10-18 | 21:30 | 45217 | 45217 | 1.5 | 4 | 1.5 | Add to_string for all types.
Mitch | 2023-10-19 | 9:30 | 2023-10-19 | 10:45 | 45218 | 45218 | 1.25 | 5 | 1.25 | Started work on hierarchy (parent/child).
Mitch | 2023-10-19 | 12:00 | 2023-10-19 | 17:50 | 45218 | 45218 | 5.8333 | 5 | 5.8333 | Work on hierarchy/relationships/transforms.
Mitch | 2023-10-19 | 19:50 | 2023-10-19 | 20:40 | 45218 | 45218 | 0.83333 | 5 | 0.83333 | Transform work.
Mitch | 2023-10-20 | 12:00 | 2023-10-20 | 17:30 | 45219 | 45219 | 5.5 | 6 | 5.5 | Finished transforms.
Mitch | 2023-10-20 | 19:30 | 2023-10-21 | 3:30 | 45219 | 45220 | 8 | 6 | 8 | Started work on UI.
Mitch | 2023-10-21 | 13:30 | 2023-10-21 | 16:00 | 45220 | 45220 | 2.5 | 7 | 2.5 | Worked on UI ordering/transparency.
Mitch | 2023-10-21 | 18:30 | 2023-10-21 | 20:00 | 45220 | 45220 | 1.5 | 7 | 1.5 | Worked on UI system.
Mitch | 2023-10-22 | 2:00 | 2023-10-22 | 2:30 | 45221 | 45221 | 0.5 | 8 | 0.5 | Worked on UI system.
Mitch | 2023-10-24 | 14:20 | 2023-10-24 | 15:10 | 45223 | 45223 | 0.83333 | 1 | 0.83333 | Worked on UI system.
Mitch | 2023-10-26 | 12:30 | 2023-10-26 | 18:15 | 45225 | 45225 | 5.75 | 1 | 5.75 | Finished UI rendering, fixed Y direction.
Mitch | 2023-11-01 | 14:00 | 2023-11-01 | 17:30 | 45231 | 45231 | 3.5 | 1 | 3.5 | Rework Material system.
Mitch | 2023-11-02 | 13:20 | 2023-11-02 | 15:00 | 45232 | 45232 | 1.6667 | 2 | 1.6667 | Rework Material system.
Mitch | 2023-11-02 | 20:50 | 2023-11-02 | 22:00 | 45232 | 45232 | 1.1667 | 2 | 1.1667 | Rework Material system.
Mitch | 2023-11-03 | 14:40 | 2023-11-03 | 15:50 | 45233 | 45233 | 1.1667 | 3 | 1.1667 | Rework Material system.
Mitch | 2023-11-06 | 16:00 | 2023-11-06 | 17:20 | 45236 | 45236 | 1.3333 | 1 | 1.3333 | Reworked buffers within Renderer.
Mitch | 2023-11-06 | 22:45 | 2023-11-07 | 0:00 | 45236 | 45237 | 1.25 | 1 | 1.25 | Buffers and materials.
Mitch | 2023-11-07 | 14:00 | 2023-11-07 | 15:10 | 45237 | 45237 | 1.1667 | 2 | 1.1667 | Worked on descriptor pooling.
Mitch | 2023-11-08 | 16:00 | 2023-11-08 | 17:25 | 45238 | 45238 | 1.4167 | 3 | 1.4167 | Worked on uniform and push constants.
Mitch | 2023-11-09 | 12:15 | 2023-11-09 | 13:45 | 45239 | 45239 | 1.5 | 4 | 1.5 | Worked on descriptor sets.
Mitch | 2023-11-10 | 12:00 | 2023-11-10 | 12:35 | 45240 | 45240 | 0.58333 | 5 | 0.58333 | Made descriptor set class.
Mitch | 2023-11-11 | 9:00 | 2023-11-11 | 12:00 | 45241 | 45241 | 3 | 6 | 3 | Worked on materials.
Mitch | 2023-11-11 | 16:00 | 2023-11-11 | 17:00 | 45241 | 45241 | 1 | 6 | 1 | Worked on materials.
Mitch | 2023-11-12 | 12:00 | 2023-11-12 | 13:35 | 45242 | 45242 | 1.5833 | 7 | 1.5833 | Worked on DescriptorSet.
Mitch | 2023-11-13 | 13:00 | 2023-11-13 | 16:00 | 45243 | 45243 | 3 | 8 | 3 | Fixed up Renderer and all related classes.
Mitch | 2023-11-13 | 21:00 | 2023-11-14 | 0:00 | 45243 | 45244 | 3 | 8 | 3 | Fixed errors.
Mitch | 2023-11-14 | 10:45 | 2023-11-14 | 15:10 | 45244 | 45244 | 4.4167 | 9 | 4.4167 | Got the program building, working on fixing test project and bugs.
Mitch | 2023-11-19 | 13:00 | 2023-11-19 | 14:00 | 45249 | 45249 | 1 | 1 | 1 | Debugging.
Mitch | 2023-11-21 | 21:00 | 2023-11-21 | 23:00 | 45251 | 45251 | 2 | 1 | 2 | Debugging, fixing descriptor set mismatches.
Mitch | 2023-11-22 | 15:30 | 2023-11-22 | 18:45 | 45252 | 45252 | 3.25 | 2 | 3.25 | Engine builds, game runs, rendering is goofed.
Mitch | 2023-11-22 | 23:00 | 2023-11-23 | 0:45 | 45252 | 45253 | 1.75 | 2 | 1.75 | Fixed test game: fixed textures, fixed rendering vertex order.
Mitch | 2023-11-23 | 10:00 | 2023-11-23 | 13:30 | 45253 | 45253 | 3.5 | 3 | 3.5 | Fixed multiple materials, generate documentation.
Mitch | 2023-11-23 | 14:00 | 2023-11-23 | 14:50 | 45253 | 45253 | 0.83333 | 3 | 0.83333 | Updated VK_ASSERT, cleaned up Github page.
Mitch | 2023-11-23 | 17:40 | 2023-11-23 | 18:40 | 45253 | 45253 | 1 | 3 | 1 | Worked on primitive types.
Mitch | 2023-11-23 | 20:00 | 2023-11-23 | 21:40 | 45253 | 45253 | 1.6667 | 3 | 1.6667 | Created Pyramid type, fixing Cube type.
Mitch | 2023-11-24 | 10:00 | 2023-11-24 | 10:40 | 45254 | 45254 | 0.66667 | 4 | 0.66667 | Working on Sphere type.
Mitch | 2023-11-25 | 10:30 | 2023-11-25 | 12:45 | 45255 | 45255 | 2.25 | 5 | 2.25 | Finished Sphere, worked on Cylinder.
Mitch | 2023-11-25 | 22:00 | 2023-11-25 | 23:55 | 45255 | 45255 | 1.9167 | 5 | 1.9167 | Updated README, fixed Cylinder and other primitive texcoords, fixed unnammed entity loading.
Mitch | 2023-11-26 | 12:15 | 2023-11-26 | 13:20 | 45256 | 45256 | 1.0833 | 6 | 1.0833 | Worked on .obj loading and resources system.
Mitch | 2023-11-26 | 21:30 | 2023-11-26 | 22:20 | 45256 | 45256 | 0.83333 | 6 | 0.83333 | Worked on .obj loading and resources system.
Mitch | 2023-12-01 | 13:35 | 2023-12-01 | 16:30 | 45261 | 45261 | 2.9167 | 1 | 2.9167 | Worked on loading Texture files, created Python script for generating C++ code.
Mitch | 2023-12-02 | 21:30 | 2023-12-02 | 23:00 | 45262 | 45262 | 1.5 | 2 | 1.5 | Worked on loading texture files.
Mitch | 2023-12-03 | 12:55 | 2023-12-03 | 15:20 | 45263 | 45263 | 2.4167 | 3 | 2.4167 | Worked on loading shaders.
Mitch | 2023-12-03 | 18:00 | 2023-12-03 | 19:00 | 45263 | 45263 | 1 | 3 | 1 | Worked on parsing files.
Mitch | 2023-12-03 | 20:00 | 2023-12-03 | 21:00 | 45263 | 45263 | 1 | 3 | 1 | Worked on expression evaluation.
Mitch | 2023-12-04 | 11:55 | 2023-12-04 | 13:40 | 45264 | 45264 | 1.75 | 4 | 1.75 | Worked on expression evaluation.
Mitch | 2023-12-04 | 16:15 | 2023-12-04 | 17:35 | 45264 | 45264 | 1.3333 | 4 | 1.3333 | Finished expression evaluation, worked on loading materials.
Mitch | 2023-12-04 | 18:40 | 2023-12-04 | 20:00 | 45264 | 45264 | 1.3333 | 4 | 1.3333 | Worked on loading models.
Mitch | 2023-12-06 | 21:00 | 2023-12-06 | 21:50 | 45266 | 45266 | 0.83333 | 1 | 0.83333 | Finished loading obj function.
Mitch | 2023-12-08 | 14:00 | 2023-12-08 | 17:00 | 45268 | 45268 | 3 | 1 | 3 | Worked on fixing test project, Dynamic deserialization.
Mitch | 2023-12-09 | 12:00 | 2023-12-09 | 14:20 | 45269 | 45269 | 2.3333 | 2 | 2.3333 | Worked on fixing test project.
Mitch | 2023-12-09 | 16:00 | 2023-12-09 | 16:45 | 45269 | 45269 | 0.75 | 2 | 0.75 | Fixed test project, all running again.
Mitch | 2023-12-09 | 18:50 | 2023-12-09 | 19:05 | 45269 | 45269 | 0.25 | 2 | 0.25 | Testing.
Mitch | 2023-12-09 | 20:45 | 2023-12-09 | 23:00 | 45269 | 45269 | 2.25 | 2 | 2.25 | Got it running but no mesh will render, so….
Mitch | 2023-12-09 | 23:40 | 2023-12-10 | 3:25 | 45269 | 45270 | 3.75 | 2 | 3.75 | Got asset loading except for models. Probably messed up obj loader.
Mitch | 2023-12-10 | 12:40 | 2023-12-10 | 14:10 | 45270 | 45270 | 1.5 | 3 | 1.5 | Model loading working!
Mitch | 2023-12-10 | 16:30 | 2023-12-10 | 17:30 | 45270 | 45270 | 1 | 3 | 1 | Worked on fixing mesh bugs.
Mitch | 2023-12-10 | 19:20 | 2023-12-10 | 21:00 | 45270 | 45270 | 1.6667 | 3 | 1.6667 | Started on audio.
Mitch | 2023-12-10 | 23:00 | 2023-12-10 | 23:45 | 45270 | 45270 | 0.75 | 3 | 0.75 | Researched audio tools.
Mitch | 2023-12-11 | 11:00 | 2023-12-11 | 15:10 | 45271 | 45271 | 4.1667 | 4 | 4.1667 | Implemented base audio tools.
Mitch | 2023-12-11 | 20:30 | 2023-12-11 | 22:40 | 45271 | 45271 | 2.1667 | 4 | 2.1667 | Worked on audio source and audio listener.
Mitch | 2023-12-12 | 9:45 | 2023-12-12 | 11:30 | 45272 | 45272 | 1.75 | 5 | 1.75 | Worked on audio sources in 3d space.
Mitch | 2023-12-12 | 21:00 | 2023-12-12 | 22:30 | 45272 | 45272 | 1.5 | 5 | 1.5 | Worked on audio sources in 3d space.
Mitch | 2023-12-13 | 9:00 | 2023-12-13 | 10:25 | 45273 | 45273 | 1.4167 | 6 | 1.4167 | Worked on audio sources in 3d space.
Mitch | 2023-12-13 | 11:00 | 2023-12-13 | 12:20 | 45273 | 45273 | 1.3333 | 6 | 1.3333 | Refactoring.
Mitch | 2023-12-13 | 13:00 | 2023-12-13 | 14:25 | 45273 | 45273 | 1.4167 | 6 | 1.4167 | Refactoring.
Mitch | 2023-12-13 | 15:45 | 2023-12-13 | 16:30 | 45273 | 45273 | 0.75 | 6 | 0.75 | Refactoring.
Mitch | 2023-12-13 | 19:00 | 2023-12-13 | 22:15 | 45273 | 45273 | 3.25 | 6 | 3.25 | Refactoring.
Mitch | 2023-12-14 | 10:25 | 2023-12-14 | 13:40 | 45274 | 45274 | 3.25 | 7 | 3.25 | Prefabs.
Mitch | 2023-12-16 | 10:15 | 2023-12-16 | 11:15 | 45276 | 45276 | 1 | 1 | 1 | Cloning.
Mitch | 2023-12-20 | 16:30 | 2023-12-20 | 17:15 | 45280 | 45280 | 0.75 | 1 | 0.75 | Rework Sprites.
Mitch | 2023-12-21 | 16:00 | 2023-12-21 | 18:00 | 45281 | 45281 | 2 | 2 | 2 | Rework sprites, research on virtual file systems.
Mitch | 2023-12-22 | 15:15 | 2023-12-22 | 16:50 | 45282 | 45282 | 1.5833 | 3 | 1.5833 | Virtual file system: Wrap.
Mitch | 2023-12-23 | 12:15 | 2023-12-23 | 15:30 | 45283 | 45283 | 3.25 | 4 | 3.25 | Virtual file system: Wrap, File, PhysicalFile, and VirtualFile.
Mitch | 2023-12-24 | 10:00 | 2023-12-24 | 16:15 | 45284 | 45284 | 6.25 | 5 | 6.25 | Virtual file system: refactoring, Wrap and Wrapper.
Mitch | 2023-12-27 | 15:30 | 2023-12-27 | 16:30 | 45287 | 45287 | 1 | 1 | 1 | Research for zlib, worked on editor application code.
Mitch | 2023-12-28 | 15:45 | 2023-12-28 | 18:40 | 45288 | 45288 | 2.9167 | 2 | 2.9167 | Wrapper and Wrap classes/files.
Mitch | 2023-12-28 | 21:35 | 2023-12-28 | 23:00 | 45288 | 45288 | 1.4167 | 2 | 1.4167 | Wrapper and Wrap classes/files.
Mitch | 2023-12-29 | 14:00 | 2023-12-29 | 15:00 | 45289 | 45289 | 1 | 3 | 1 | Wrapper and Wrap classes/files.
Mitch | 2023-12-29 | 23:40 | 2023-12-30 | 0:00 | 45289 | 45290 | 0.33333 | 3 | 0.33333 | Wrapper and Wrap classes/files.
Mitch | 2023-12-30 | 13:30 | 2023-12-30 | 15:30 | 45290 | 45290 | 2 | 4 | 2 | Wrapper and Wrap classes/files.
Mitch | 2023-12-30 | 23:30 | 2023-12-31 | 1:00 | 45290 | 45291 | 1.5 | 4 | 1.5 | Wrap
Mitch | 2023-12-31 | 16:20 | 2023-12-31 | 18:00 | 45291 | 45291 | 1.6667 | 5 | 1.6667 | Wrap
Mitch | 2024-01-01 | 15:40 | 2024-01-01 | 17:15 | 45292 | 45292 | 1.5833 | 6 | 1.5833 | Wrap
Mitch | 2024-01-03 | 18:30 | 2024-01-03 | 21:00 | 45294 | 45294 | 2.5 | 1 | 2.5 | Wrap
Mitch | 2024-01-04 | 12:30 | 2024-01-04 | 17:15 | 45295 | 45295 | 4.75 | 2 | 4.75 | Finished Wrap, or at least its good enough for now.
Mitch | 2024-01-04 | 22:10 | 2024-01-05 | 0:30 | 45295 | 45296 | 2.3333 | 2 | 2.3333 | Finish up Wrap, redo Wrapper, add compression.
Mitch | 2024-01-06 | 15:15 | 2024-01-06 | 17:15 | 45297 | 45297 | 2 | 1 | 2 | Wrap compression.
Mitch | 2024-01-09 | 11:15 | 2024-01-09 | 16:30 | 45300 | 45300 | 5.25 | 1 | 5.25 | Finished wrap, start on redo Sprite.
Mitch | 2024-01-10 | 18:00 | 2024-01-10 | 21:00 | 45301 | 45301 | 3 | 2 | 3 | Work on Sprites, redo descriptor sets.
Mitch | 2024-01-11 | 7:30 | 2024-01-11 | 8:30 | 45302 | 45302 | 1 | 3 | 1 | Work on Sprites, redo descriptor sets.
Mitch | 2024-01-11 | 13:30 | 2024-01-11 | 14:40 | 45302 | 45302 | 1.1667 | 3 | 1.1667 | Work on descriptor sets.
Mitch | 2024-01-11 | 16:45 | 2024-01-11 | 17:30 | 45302 | 45302 | 0.75 | 3 | 0.75 | Bug fixing.
Mitch | 2024-01-11 | 19:00 | 2024-01-11 | 21:00 | 45302 | 45302 | 2 | 3 | 2 | Bug fixing.
Mitch | 2024-01-12 | 11:00 | 2024-01-12 | 17:30 | 45303 | 45303 | 6.5 | 4 | 6.5 | Bug fixing. Descriptor sets reworked.
Mitch | 2024-01-12 | 17:30 | 2024-01-12 | 18:30 | 45303 | 45303 | 1 | 4 | 1 | Got a Sprite rendering.
Mitch | 2024-01-12 | 22:30 | 2024-01-13 | 2:00 | 45303 | 45304 | 3.5 | 4 | 3.5 | TextureAtlas.
Mitch | 2024-01-13 | 12:00 | 2024-01-13 | 14:00 | 45304 | 45304 | 2 | 5 | 2 | Testing texture atlas, research.
Mitch | 2024-01-13 | 21:00 | 2024-01-13 | 22:45 | 45304 | 45304 | 1.75 | 5 | 1.75 | TextureAtlas.
Mitch | 2024-01-14 | 22:00 | 2024-01-14 | 23:30 | 45305 | 45305 | 1.5 | 6 | 1.5 | Sprite bug fixes.
Mitch | 2024-01-15 | 0:15 | 2024-01-15 | 2:15 | 45306 | 45306 | 2 | 7 | 2 | Finite state machine.
Mitch | 2024-01-15 | 13:20 | 2024-01-15 | 14:30 | 45306 | 45306 | 1.1667 | 7 | 1.1667 | Animation/animator.
Mitch | 2024-01-16 | 8:30 | 2024-01-16 | 10:00 | 45307 | 45307 | 1.5 | 8 | 1.5 | Animation.
Mitch | 2024-01-16 | 13:10 | 2024-01-16 | 14:30 | 45307 | 45307 | 1.3333 | 8 | 1.3333 | Fix FSM.
Mitch | 2024-01-16 | 16:00 | 2024-01-16 | 16:30 | 45307 | 45307 | 0.5 | 8 | 0.5 | Fix FSM.
Mitch | 2024-01-17 | 14:30 | 2024-01-17 | 16:20 | 45308 | 45308 | 1.8333 | 9 | 1.8333 | Animator serialization.
Mitch | 2024-01-17 | 19:30 | 2024-01-17 | 23:30 | 45308 | 45308 | 4 | 9 | 4 | FSM and Registry serialization.
Mitch | 2024-01-18 | 9:30 | 2024-01-18 | 10:45 | 45309 | 45309 | 1.25 | 10 | 1.25 | Vector structs.
Mitch | 2024-01-18 | 10:55 | 2024-01-18 | 13:10 | 45309 | 45309 | 2.25 | 10 | 2.25 | Serialization.
Mitch | 2024-01-19 | 14:00 | 2024-01-19 | 17:40 | 45310 | 45310 | 3.6667 | 11 | 3.6667 | Bug fixes.
Mitch | 2024-01-19 | 19:50 | 2024-01-19 | 21:45 | 45310 | 45310 | 1.9167 | 11 | 1.9167 | Bug fixes, animator serialization.
Mitch | 2024-01-20 | 15:00 | 2024-01-20 | 16:25 | 45311 | 45311 | 1.4167 | 12 | 1.4167 | Bug fixes, node write and read.
Mitch | 2024-01-20 | 22:25 | 2024-01-20 | 23:10 | 45311 | 45311 | 0.75 | 12 | 0.75 | Animator.
Mitch | 2024-01-21 | 14:30 | 2024-01-21 | 17:15 | 45312 | 45312 | 2.75 | 13 | 2.75 | Serialization, again. Ugh.
Mitch | 2024-01-21 | 20:55 | 2024-01-21 | 23:10 | 45312 | 45312 | 2.25 | 13 | 2.25 | Refactoring, bug fixing.
Mitch | 2024-01-22 | 13:20 | 2024-01-22 | 14:00 | 45313 | 45313 | 0.66667 | 14 | 0.66667 | Bug fixes.
Mitch | 2024-01-22 | 15:10 | 2024-01-22 | 17:00 | 45313 | 45313 | 1.8333 | 14 | 1.8333 | Bug fixes.
Mitch | 2024-01-22 | 18:00 | 2024-01-22 | 23:45 | 45313 | 45313 | 5.75 | 14 | 5.75 | Bug fixes.
Mitch | 2024-01-23 | 9:30 | 2024-01-23 | 10:35 | 45314 | 45314 | 1.0833 | 15 | 1.0833 | Refactor Register, Scene.
Mitch | 2024-01-23 | 10:45 | 2024-01-23 | 15:25 | 45314 | 45314 | 4.6667 | 15 | 4.6667 | Bug fixes.
Mitch | 2024-01-23 | 15:35 | 2024-01-23 | 16:55 | 45314 | 45314 | 1.3333 | 15 | 1.3333 | Bug fixes.
Mitch | 2024-01-23 | 20:30 | 2024-01-23 | 23:25 | 45314 | 45314 | 2.9167 | 15 | 2.9167 | Fixed program, Animation design.
Mitch | 2024-01-24 | 19:20 | 2024-01-24 | 23:00 | 45315 | 45315 | 3.6667 | 16 | 3.6667 | Rework animations.
Mitch | 2024-01-24 | 23:25 | 2024-01-25 | 4:40 | 45315 | 45316 | 5.25 | 16 | 5.25 | Finish animation rework.
Mitch | 2024-01-25 | 13:10 | 2024-01-25 | 17:10 | 45316 | 45316 | 4 | 17 | 4 | Animator.
Mitch | 2024-01-25 | 22:25 | 2024-01-25 | 23:45 | 45316 | 45316 | 1.3333 | 17 | 1.3333 | Animation lerping rework.
Mitch | 2024-02-07 | 11:00 | 2024-02-07 | 17:00 | 45329 | 45329 | 6 | 1 | 6 | Animations.
Mitch | 2024-02-07 | 19:30 | 2024-02-07 | 22:00 | 45329 | 45329 | 2.5 | 1 | 2.5 | Animations now deserialize into anything.
Mitch | 2024-02-08 | 12:30 | 2024-02-08 | 15:45 | 45330 | 45330 | 3.25 | 2 | 3.25 | Refactoring.
Mitch | 2024-02-08 | 16:00 | 2024-02-08 | 17:15 | 45330 | 45330 | 1.25 | 2 | 1.25 | Editor menu items & project loading.
Mitch | 2024-02-09 | 11:00 | 2024-02-09 | 12:30 | 45331 | 45331 | 1.5 | 3 | 1.5 | Editor project loading.
Mitch | 2024-02-09 | 13:00 | 2024-02-09 | 14:00 | 45331 | 45331 | 1 | 3 | 1 | Editor scene loading.
Mitch | 2024-02-09 | 14:25 | 2024-02-09 | 16:35 | 45331 | 45331 | 2.1667 | 3 | 2.1667 | Redo engine/runtime to work with editor.
Mitch | 2024-02-10 | 12:00 | 2024-02-10 | 16:40 | 45332 | 45332 | 4.6667 | 4 | 4.6667 | Restructure runtime to work with editor better, editor windows.
Mitch | 2024-02-10 | 18:10 | 2024-02-10 | 20:40 | 45332 | 45332 | 2.5 | 4 | 2.5 | Assets window.
Mitch | 2024-02-12 | 11:00 | 2024-02-12 | 18:00 | 45334 | 45334 | 7 | 1 | 7 | Restructure runtime to work with editor better.
Mitch | 2024-02-12 | 22:00 | 2024-02-13 | 0:00 | 45334 | 45335 | 2 | 1 | 2 | Work towards loading and editing scenes.
Mitch | 2024-02-13 | 15:00 | 2024-02-13 | 16:25 | 45335 | 45335 | 1.4167 | 2 | 1.4167 | Started adding Mono to the Runtime.
Mitch | 2024-02-13 | 20:30 | 2024-02-14 | 1:15 | 45335 | 45336 | 4.75 | 2 | 4.75 | Added Mono to the Runtime, Assembly.
Mitch | 2024-02-14 | 15:45 | 2024-02-14 | 16:45 | 45336 | 45336 | 1 | 3 | 1 | Research on scripting. Thanks Cherno.
Mitch | 2024-02-14 | 21:00 | 2024-02-15 | 1:35 | 45336 | 45337 | 4.5833 | 3 | 4.5833 | Serialization for Scripts, assembly loading.
Mitch | 2024-02-15 | 11:30 | 2024-02-15 | 17:00 | 45337 | 45337 | 5.5 | 4 | 5.5 | Script component and system.
Mitch | 2024-02-15 | 23:00 | 2024-02-16 | 2:30 | 45337 | 45338 | 3.5 | 4 | 3.5 | Script events.
Mitch | 2024-02-15 | 10:00 | 2024-02-15 | 13:00 | 45337 | 45337 | 3 | 4 | 3 | UUIDs.
Mitch | 2024-02-16 | 14:30 | 2024-02-16 | 15:30 | 45338 | 45338 | 1 | 5 | 1 | UUIDs.
Mitch | 2024-02-16 | 16:30 | 2024-02-16 | 17:50 | 45338 | 45338 | 1.3333 | 5 | 1.3333 | Start C# -> C++ function calling.
Mitch | 2024-02-16 | 22:00 | 2024-02-17 | 1:30 | 45338 | 45339 | 3.5 | 5 | 3.5 | C#/C++ Console, start on Entity.
Mitch | 2024-02-17 | 8:00 | 2024-02-17 | 11:00 | 45339 | 45339 | 3 | 6 | 3 | Component scripting.
Mitch | 2024-02-17 | 12:00 | 2024-02-17 | 14:30 | 45339 | 45339 | 2.5 | 6 | 2.5 | Script refactoring.
Mitch | 2024-02-17 | 16:00 | 2024-02-17 | 17:30 | 45339 | 45339 | 1.5 | 6 | 1.5 | Assertions and macros.
Mitch | 2024-02-17 | 23:00 | 2024-02-18 | 2:00 | 45339 | 45340 | 3 | 6 | 3 | Fix assertions, debug scripting.
Mitch | 2024-02-18 | 23:45 | 2024-02-19 | 4:50 | 45340 | 45341 | 5.0833 | 7 | 5.0833 | Debug why the hell value types aren't initialized in scripts.
Mitch | 2024-02-19 | 13:20 | 2024-02-19 | 18:00 | 45341 | 45341 | 4.6667 | 8 | 4.6667 | Stupid ass Mono scripting debugging. Entity class members throw exceptions.
Mitch | 2024-02-19 | 22:00 | 2024-02-20 | 4:30 | 45341 | 45342 | 6.5 | 8 | 6.5 | Fixed that stupid ass bug, added get/add/rem component scripting functionality.
Mitch | 2024-02-21 | 0:00 | 2024-02-21 | 4:00 | 45343 | 45343 | 4 | 1 | 4 | Script linking.
Mitch | 2024-02-21 | 13:35 | 2024-02-21 | 18:00 | 45343 | 45343 | 4.4167 | 1 | 4.4167 | Fix remove component, add time.
Mitch | 2024-02-22 | 13:00 | 2024-02-22 | 15:10 | 45344 | 45344 | 2.1667 | 2 | 2.1667 | Enable/disable entities, debug transform get position.
Mitch | 2024-02-22 | 21:00 | 2024-02-23 | 4:15 | 45344 | 45345 | 7.25 | 2 | 7.25 | Fix transform get position, add input to C#.
Mitch | 2024-02-23 | 11:00 | 2024-02-23 | 17:15 | 45345 | 45345 | 6.25 | 3 | 6.25 | Bug fixes, cursor mode, parenting.
Mitch | 2024-02-24 | 0:15 | 2024-02-24 | 2:40 | 45346 | 45346 | 2.4167 | 4 | 2.4167 | Fix scene loading in editor.
Mitch | 2024-02-25 | 14:30 | 2024-02-25 | 17:15 | 45347 | 45347 | 2.75 | 5 | 2.75 | Debug heap corruption (SystemRegistry -_-)
Mitch | 2024-02-26 | 12:00 | 2024-02-26 | 18:15 | 45348 | 45348 | 6.25 | 6 | 6.25 | Fix bugs, revamped input system, create icon, create theme (wip)
Mitch | 2024-02-26 | 21:00 | 2024-02-27 | 3:45 | 45348 | 45349 | 6.75 | 6 | 6.75 | Hierarchy and properties windows, fix sorting, add tags, fix bugs.
Mitch | 2024-02-27 | 13:00 | 2024-02-27 | 14:30 | 45349 | 45349 | 1.5 | 7 | 1.5 | Edit/add/remove components.
Mitch | 2024-02-27 | 19:00 | 2024-02-27 | 20:00 | 45349 | 45349 | 1 | 7 | 1 | Work on hierarchy menu items.
Mitch | 2024-02-27 | 20:30 | 2024-02-27 | 21:30 | 45349 | 45349 | 1 | 7 | 1 | Work on hierarchy menu items.
Mitch | 2024-02-28 | 13:00 | 2024-02-28 | 18:05 | 45350 | 45350 | 5.0833 | 8 | 5.0833 | Asset engine.
Mitch | 2024-02-28 | 19:15 | 2024-02-28 | 23:20 | 45350 | 45350 | 4.0833 | 8 | 4.0833 | Asset major refactor.
Mitch | 2024-02-29 | 10:30 | 2024-02-29 | 15:00 | 45351 | 45351 | 4.5 | 9 | 4.5 | Bug fix refactor.
Mitch | 2024-03-02 | 0:30 | 2024-03-02 | 3:30 | 45353 | 45353 | 3 | 1 | 3 | Asset engine complete: UUIDs used for all assets and entities.
Mitch | 2024-03-02 | 17:00 | 2024-03-02 | 18:00 | 45353 | 45353 | 1 | 1 | 1 | Fix editor UUIDs.
Mitch | 2024-03-03 | 10:30 | 2024-03-03 | 11:55 | 45354 | 45354 | 1.4167 | 2 | 1.4167 | Quaternion/euler angles, start fix scene create/load.
Mitch | 2024-03-04 | 16:40 | 2024-03-04 | 17:40 | 45355 | 45355 | 1 | 3 | 1 | Fix scene create/load.
Mitch | 2024-03-04 | 20:00 | 2024-03-05 | 2:40 | 45355 | 45356 | 6.6667 | 3 | 6.6667 | Scene preview.
Mitch | 2024-03-05 | 11:00 | 2024-03-05 | 17:30 | 45356 | 45356 | 6.5 | 4 | 6.5 | Many small editor improvements.
Mitch | 2024-03-06 | 13:00 | 2024-03-06 | 14:00 | 45357 | 45357 | 1 | 5 | 1 | Application, implement into Editor.
Mitch | 2024-03-06 | 20:00 | 2024-03-07 | 3:50 | 45357 | 45358 | 7.8333 | 5 | 7.8333 | Build to Wrap files, use those, fix test project, independent builds.
Mitch | 2024-03-07 | 20:00 | 2024-03-07 | 21:15 | 45358 | 45358 | 1.25 | 6 | 1.25 | Fix deletion, work on double click focus.
Mitch | 2024-03-11 | 10:00 | 2024-03-11 | 11:00 | 45362 | 45362 | 1 | 1 | 1 | Ignore double click. Start save scene.
Mitch | 2024-03-11 | 15:00 | 2024-03-11 | 17:40 | 45362 | 45362 | 2.6667 | 1 | 2.6667 | Save scene, fix entity paste.
Mitch | 2024-03-11 | 22:00 | 2024-03-11 | 23:00 | 45362 | 45362 | 1 | 1 | 1 | Bug fixes.
Mitch | 2024-03-13 | 10:30 | 2024-03-13 | 12:30 | 45364 | 45364 | 2 | 1 | 2 | Serializing/deserializing full names, start on script loading.
Mitch | 2024-03-14 | 11:00 | 2024-03-14 | 12:10 | 45365 | 45365 | 1.1667 | 2 | 1.1667 | C# assembly creation from editor.
Mitch | 2024-03-14 | 21:00 | 2024-03-15 | 2:00 | 45365 | 45366 | 5 | 2 | 5 | Fix script serialization, asset loading, project create.
Mitch | 2024-03-15 | 14:30 | 2024-03-15 | 17:00 | 45366 | 45366 | 2.5 | 3 | 2.5 | Work on fix Vulkan close errors.
Mitch | 2024-03-15 | 20:00 | 2024-03-15 | 22:15 | 45366 | 45366 | 2.25 | 3 | 2.25 | Debug Vulkan errors.
Mitch | 2024-03-18 | 12:15 | 2024-03-18 | 12:50 | 45369 | 45369 | 0.58333 | 1 | 0.58333 | Debug Vulkan errors.
Mitch | 2024-03-18 | 21:30 | 2024-03-19 | 3:05 | 45369 | 45370 | 5.5833 | 1 | 5.5833 | Fix errors, redo asset loading, asset property window.
Mitch | 2024-03-19 | 10:00 | 2024-03-19 | 12:30 | 45370 | 45370 | 2.5 | 2 | 2.5 | Asset loading/unloading, fix errors.
Mitch | 2024-03-20 | 19:00 | 2024-03-20 | 21:35 | 45371 | 45371 | 2.5833 | 3 | 2.5833 | Asset loading/unloading.
Mitch | 2024-03-21 | 12:15 | 2024-03-21 | 12:50 | 45372 | 45372 | 0.58333 | 4 | 0.58333 | C# link Camera.
Mitch | 2024-03-29 | 0:00 | 2024-03-29 | 3:30 | 45380 | 45380 | 3.5 | 1 | 3.5 | Fix loading issues, Relationship C#.
Mitch | 2024-04-01 | 22:30 | 2024-04-02 | 2:50 | 45383 | 45384 | 4.3333 | 1 | 4.3333 | Remove Relationship C#, add to Entity, Wrapper program.
Mitch | 2024-04-02 | 14:30 | 2024-04-02 | 17:05 | 45384 | 45384 | 2.5833 | 2 | 2.5833 | Add Data folder to copy engine files from, work on Sprites.
Mitch | 2024-04-02 | 21:30 | 2024-04-02 | 22:30 | 45384 | 45384 | 1 | 2 | 1 | Bug fixes.
Mitch | 2024-04-04 | 14:05 | 2024-04-04 | 17:45 | 45386 | 45386 | 3.6667 | 1 | 3.6667 | Wrapper improvements, BuiltIn asset loading.
Mitch | 2024-04-04 | 23:00 | 2024-04-05 | 1:00 | 45386 | 45387 | 2 | 1 | 2 | Start controller inputs.
Mitch | 2024-04-05 | 11:00 | 2024-04-05 | 17:05 | 45387 | 45387 | 6.0833 | 2 | 6.0833 | Controller inputs, start fix UI.
Mitch | 2024-04-05 | 22:30 | 2024-04-06 | 2:30 | 45387 | 45388 | 4 | 2 | 4 | Fixing UI.
Mitch | 2024-04-06 | 11:50 | 2024-04-06 | 16:00 | 45388 | 45388 | 4.1667 | 3 | 4.1667 | Fix UI, UI stretching, Sprite coloring, UI mouse detection.
Mitch | 2024-04-06 | 21:00 | 2024-04-07 | 3:45 | 45388 | 45389 | 6.75 | 3 | 6.75 | UI mouse events, editor bug fixes and improvements.
Mitch | 2024-04-07 | 15:05 | 2024-04-07 | 17:10 | 45389 | 45389 | 2.0833 | 4 | 2.0833 | Fix rendering sorting order.
Mitch | 2024-04-08 | 19:30 | 2024-04-08 | 22:00 | 45390 | 45390 | 2.5 | 5 | 2.5 | Templates for new assets, bug fixes.
Mitch | 2024-04-09 | 0:05 | 2024-04-09 | 4:00 | 45391 | 45391 | 3.9167 | 6 | 3.9167 | FileWatcher, reduce build times.
Mitch | 2024-04-09 | 12:45 | 2024-04-09 | 15:50 | 45391 | 45391 | 3.0833 | 6 | 3.0833 | Editor improvements.
Mitch | 2024-04-10 | 0:00 | 2024-04-10 | 3:10 | 45392 | 45392 | 3.1667 | 7 | 3.1667 | Debug, Logger.
Mitch | 2024-04-11 | 1:00 | 2024-04-11 | 3:00 | 45393 | 45393 | 2 | 8 | 2 | Bug fixing.
Mitch | 2024-04-11 | 14:45 | 2024-04-11 | 15:00 | 45393 | 45393 | 0.25 | 8 | 0.25 | Installation work.
Mitch | 2024-05-06 | 14:00 | 2024-05-06 | 14:30 | 45418 | 45418 | 0.5 | 1 | 0.5 | Bug fixes.
Mitch | 2024-05-06 | 21:00 | 2024-05-06 | 21:45 | 45418 | 45418 | 0.75 | 1 | 0.75 | Bug fixes.
Mitch | 2024-05-07 | 10:15 | 2024-05-07 | 11:35 | 45419 | 45419 | 1.3333 | 2 | 1.3333 | Bug fixes.
Mitch | 2024-05-07 | 23:30 | 2024-05-08 | 1:00 | 45419 | 45420 | 1.5 | 2 | 1.5 | Bug fixes.
Mitch | 2024-05-08 | 2:00 | 2024-05-08 | 3:00 | 45420 | 45420 | 1 | 3 | 1 | Bug fixes.
Mitch | 2024-05-19 | 10:00 | 2024-05-19 | 13:00 | 45431 | 45431 | 3 | 1 | 3 | Font rendering.
Mitch | 2024-05-19 | 15:00 | 2024-05-19 | 16:50 | 45431 | 45431 | 1.8333 | 1 | 1.8333 | Font rendering.
Mitch | 2024-05-19 | 17:40 | 2024-05-19 | 18:10 | 45431 | 45431 | 0.5 | 1 | 0.5 | Font rendering.
Mitch | 2024-05-20 | 23:00 | 2024-05-21 | 0:30 | 45432 | 45433 | 1.5 | 2 | 1.5 | Overhaul.
Mitch | 2024-05-21 | 20:00 | 2024-05-22 | 1:10 | 45433 | 45434 | 5.1667 | 3 | 5.1667 | Overhaul.
Mitch | 2024-05-22 | 18:00 | 2024-05-23 | 1:30 | 45434 | 45435 | 7.5 | 4 | 7.5 | Overhaul.
Mitch | 2024-05-22 | 22:00 | 2024-05-24 | 1:45 | 45434 | 45436 | 27.75 | 4 | 27.75 | Overhaul.
Mitch | 2024-05-25 | 22:00 | 2024-05-26 | 0:30 | 45437 | 45438 | 2.5 | 1 | 2.5 | Overhaul. Smart pointers.
Mitch | 2025-05-26 | 11:00 | 2025-05-26 | 12:30 | 45803 | 45803 | 1.5 | 1 | 1.5 | Bug fixes.
Mitch | 2024-05-26 | 15:30 | 2024-05-26 | 17:00 | 45438 | 45438 | 1.5 | 1 | 1.5 | Bug fixes.
Mitch | 2024-05-26 | 20:55 | 2024-05-26 | 22:45 | 45438 | 45438 | 1.8333 | 1 | 1.8333 | Bug fixes.
Mitch | 2024-05-27 | 19:10 | 2024-05-27 | 23:30 | 45439 | 45439 | 4.3333 | 2 | 4.3333 | Bug fixes, remove absolute paths.
Mitch | 2024-05-30 | 20:00 | 2024-05-30 | 21:00 | 45442 | 45442 | 1 | 1 | 1 | Bug fixes.
Mitch | 2024-05-31 | 22:30 | 2024-05-31 | 23:10 | 45443 | 45443 | 0.66667 | 2 | 0.66667 | Test on PC. Fail.
Mitch | 2024-06-01 | 10:00 | 2024-06-01 | 12:30 | 45444 | 45444 | 2.5 | 3 | 2.5 | Test on PC. Success!
Mitch | 2024-06-01 | 14:40 | 2024-06-01 | 15:30 | 45444 | 45444 | 0.83333 | 3 | 0.83333 | Bug fixes.
Mitch | 2024-06-03 | 22:00 | 2024-06-04 | 0:30 | 45446 | 45447 | 2.5 | 1 | 2.5 | Test on PC, without Vulkan. Success!
Mitch | 2024-06-06 | 14:00 | 2024-06-06 | 18:10 | 45449 | 45449 | 4.1667 | 1 | 4.1667 | Optimizations, bug fixes, work on sorting, again.
Mitch | 2024-06-08 | 17:35 | 2024-06-08 | 17:55 | 45451 | 45451 | 0.33333 | 1 | 0.33333 | Fix entity sorting.
Mitch | 2024-06-08 | 21:30 | 2024-06-08 | 22:30 | 45451 | 45451 | 1 | 1 | 1 | Bug fixes.
Mitch | 2024-06-10 | 21:00 | 2024-06-10 | 22:45 | 45453 | 45453 | 1.75 | 1 | 1.75 | Bug fixes.
Mitch | 2024-06-11 | 19:00 | 2024-06-11 | 21:00 | 45454 | 45454 | 2 | 2 | 2 | Font loading.
Mitch | 2024-06-12 | 18:30 | 2024-06-12 | 22:45 | 45455 | 45455 | 4.25 | 3 | 4.25 | Font loading.
Mitch | 2024-06-14 | 16:45 | 2024-06-14 | 17:50 | 45457 | 45457 | 1.0833 | 1 | 1.0833 | Font rendering.
Mitch | 2024-06-14 | 21:00 | 2024-06-14 | 23:00 | 45457 | 45457 | 2 | 1 | 2 | Font rendering.
Mitch | 2024-06-15 | 11:45 | 2024-06-15 | 14:50 | 45458 | 45458 | 3.0833 | 2 | 3.0833 | Font rendering.
Mitch | 2024-06-15 | 19:15 | 2024-06-15 | 20:30 | 45458 | 45458 | 1.25 | 2 | 1.25 | Debugging.
Mitch | 2024-06-17 | 17:00 | 2024-06-17 | 18:00 | 45460 | 45460 | 1 | 1 | 1 | Debugging.
Mitch | 2024-06-18 | 20:00 | 2024-06-18 | 21:00 | 45461 | 45461 | 1 | 2 | 1 | Debugging.
Mitch | 2024-06-19 | 21:30 | 2024-06-20 | 0:30 | 45462 | 45463 | 3 | 3 | 3 | Font rendering.
Mitch | 2024-06-20 | 20:10 | 2024-06-20 | 21:20 | 45463 | 45463 | 1.1667 | 4 | 1.1667 | Reflection.
Mitch | 2024-06-24 | 14:45 | 2024-06-24 | 16:15 | 45467 | 45467 | 1.5 | 1 | 1.5 | Reflection.
Mitch | 2024-06-27 | 21:00 | 2024-06-27 | 22:50 | 45470 | 45470 | 1.8333 | 1 | 1.8333 | Font rendering transparency.
Mitch | 2024-06-29 | 14:30 | 2024-06-29 | 15:30 | 45472 | 45472 | 1 | 1 | 1 | Finish text rendering.
Mitch | 2024-06-29 | 16:30 | 2024-06-29 | 18:30 | 45472 | 45472 | 2 | 1 | 2 | Bug fixes.
Mitch | 2024-07-01 | 17:50 | 2024-07-01 | 18:55 | 45474 | 45474 | 1.0833 | 1 | 1.0833 | Add sprite template, bug fixes.
Mitch | 2024-08-03 | 22:00 | 2024-08-04 | 1:00 | 45507 | 45508 | 3 | 1 | 3 | Bug fixes.
Mitch | 2024-08-04 | 12:40 | 2024-08-04 | 13:25 | 45508 | 45508 | 0.75 | 2 | 0.75 | Bug fixes.
Mitch | 2024-08-04 | 16:30 | 2024-08-04 | 17:15 | 45508 | 45508 | 0.75 | 2 | 0.75 | Bug fixes.
Mitch | 2024-08-04 | 19:00 | 2024-08-04 | 22:15 | 45508 | 45508 | 3.25 | 2 | 3.25 | Orthographic camera, bug fixes.
Mitch | 2024-08-05 | 17:45 | 2024-08-05 | 18:15 | 45509 | 45509 | 0.5 | 3 | 0.5 | Bug fixes.
Mitch | 2024-08-05 | 21:00 | 2024-08-06 | 0:45 | 45509 | 45510 | 3.75 | 3 | 3.75 | Bug fixes.
Mitch | 2024-08-06 | 19:30 | 2024-08-06 | 20:10 | 45510 | 45510 | 0.66667 | 4 | 0.66667 | Scripting: main camera.
Mitch | 2024-08-11 | 9:00 | 2024-08-11 | 10:10 | 45515 | 45515 | 1.1667 | 1 | 1.1667 | Scripting: global transform gets.
Mitch | 2024-08-11 | 10:10 | 2024-08-11 | 10:40 | 45515 | 45515 | 0.5 | 1 | 0.5 | Add warnings for incorrect material/template values.
Mitch | 2024-08-11 | 16:00 | 2024-08-11 | 17:00 | 45515 | 45515 | 1 | 1 | 1 | Research: physics.
Mitch | 2024-08-11 | 22:40 | 2024-08-11 | 23:35 | 45515 | 45515 | 0.91667 | 1 | 0.91667 | Research: physics.
Mitch | 2024-08-20 | 18:30 | 2024-08-20 | 19:05 | 45524 | 45524 | 0.58333 | 1 | 0.58333 | Physics.
Mitch | 2024-08-20 | 19:10 | 2024-08-20 | 21:00 | 45524 | 45524 | 1.8333 | 1 | 1.8333 | Physics.
Mitch | 2024-08-21 | 22:00 | 2024-08-22 | 0:00 | 45525 | 45526 | 2 | 2 | 2 | Physics, raycasting.
Mitch | 2024-08-22 | 18:20 | 2024-08-22 | 20:20 | 45526 | 45526 | 2 | 3 | 2 | Physics, raycasting.
Mitch | 2024-08-26 | 21:00 | 2024-08-26 | 23:00 | 45530 | 45530 | 2 | 1 | 2 | Refactoring.
Mitch | 2024-08-27 | 19:00 | 2024-08-28 | 2:00 | 45531 | 45532 | 7 | 2 | 7 | Refactoring.
Mitch | 2024-08-28 | 21:00 | 2024-08-28 | 23:20 | 45532 | 45532 | 2.3333 | 3 | 2.3333 | Refactoring.
Mitch | 2024-08-29 | 13:00 | 2024-08-29 | 15:30 | 45533 | 45533 | 2.5 | 4 | 2.5 | Refactoring.
Mitch | 2024-08-29 | 16:30 | 2024-08-29 | 17:45 | 45533 | 45533 | 1.25 | 4 | 1.25 | Refactoring.
Mitch | 2024-08-29 | 18:30 | 2024-08-29 | 21:40 | 45533 | 45533 | 3.1667 | 4 | 3.1667 | Refactoring.
Mitch | 2024-08-29 | 23:30 | 2024-08-30 | 1:00 | 45533 | 45534 | 1.5 | 4 | 1.5 | Refactoring.
Mitch | 2024-09-02 | 12:00 | 2024-09-02 | 13:00 | 45537 | 45537 | 1 | 1 | 1 | Refactoring.
Mitch | 2024-09-03 | 18:00 | 2024-09-03 | 20:30 | 45538 | 45538 | 2.5 | 2 | 2.5 | Refactoring.
Mitch | 2024-09-03 | 23:00 | 2024-09-04 | 1:40 | 45538 | 45539 | 2.6667 | 2 | 2.6667 | Refactoring.
Mitch | 2024-09-04 | 19:00 | 2024-09-04 | 22:00 | 45539 | 45539 | 3 | 3 | 3 | Refactoring.
Mitch | 2024-09-06 | 0:00 | 2024-09-06 | 2:55 | 45541 | 45541 | 2.9167 | 1 | 2.9167 | Refactoring.
Mitch | 2024-09-06 | 17:30 | 2024-09-06 | 18:30 | 45541 | 45541 | 1 | 1 | 1 | Refactoring.
Mitch | 2024-09-08 | 15:45 | 2024-09-08 | 17:00 | 45543 | 45543 | 1.25 | 1 | 1.25 | Refactoring.
Mitch | 2024-09-08 | 17:35 | 2024-09-09 | 1:25 | 45543 | 45544 | 7.8333 | 1 | 7.8333 | Refactoring.
Mitch | 2024-09-10 | 21:00 | 2024-09-11 | 1:00 | 45545 | 45546 | 4 | 1 | 4 | Traingle rendering.
Mitch | 2024-09-12 | 21:00 | 2024-09-13 | 1:55 | 45547 | 45548 | 4.9167 | 1 | 4.9167 | Shaders and mesh.
Mitch | 2024-09-13 | 21:00 | 2024-09-14 | 0:50 | 45548 | 45549 | 3.8333 | 2 | 3.8333 | Buffers and mesh indices.
Mitch | 2024-09-15 | 23:00 | 2024-09-16 | 1:20 | 45550 | 45551 | 2.3333 | 1 | 2.3333 | Descriptor sets, constants.
Mitch | 2024-09-16 | 23:00 | 2024-09-17 | 1:40 | 45551 | 45552 | 2.6667 | 2 | 2.6667 | Descriptor sets.
Mitch | 2024-09-17 | 20:00 | 2024-09-18 | 0:30 | 45552 | 45553 | 4.5 | 3 | 4.5 | Textures.
Mitch | 2024-09-18 | 21:00 | 2024-09-19 | 1:00 | 45553 | 45554 | 4 | 4 | 4 | Textures.
Mitch | 2024-09-19 | 22:30 | 2024-09-20 | 1:45 | 45554 | 45555 | 3.25 | 5 | 3.25 | Refactoring.
Mitch | 2024-09-20 | 17:30 | 2024-09-20 | 19:00 | 45555 | 45555 | 1.5 | 6 | 1.5 | Depth buffering.
Mitch | 2024-09-21 | 12:00 | 2024-09-21 | 13:40 | 45556 | 45556 | 1.6667 | 7 | 1.6667 | Bug fixes.
Mitch | 2024-09-22 | 4:00 | 2024-09-22 | 7:20 | 45557 | 45557 | 3.3333 | 8 | 3.3333 | Serialization.
Mitch | 2024-09-22 | 14:00 | 2024-09-22 | 15:00 | 45557 | 45557 | 1 | 8 | 1 | Bug fixes.
Mitch | 2024-09-22 | 16:30 | 2024-09-22 | 18:30 | 45557 | 45557 | 2 | 8 | 2 | Bug fixes.
Mitch | 2024-09-22 | 21:00 | 2024-09-22 | 22:35 | 45557 | 45557 | 1.5833 | 8 | 1.5833 | Mesh shapes.
Mitch | 2024-09-23 | 22:00 | 2024-09-24 | 1:30 | 45558 | 45559 | 3.5 | 9 | 3.5 | Serialization.
Mitch | 2024-09-24 | 21:45 | 2024-09-25 | 2:45 | 45559 | 45560 | 5 | 10 | 5 | Serialization.
Mitch | 2024-09-25 | 22:00 | 2024-09-26 | 1:10 | 45560 | 45561 | 3.1667 | 11 | 3.1667 | Refactoring.
Mitch | 2024-09-26 | 18:00 | 2024-09-26 | 18:20 | 45561 | 45561 | 0.33333 | 12 | 0.33333 | Reader.
Mitch | 2024-09-29 | 10:30 | 2024-09-29 | 18:00 | 45564 | 45564 | 7.5 | 1 | 7.5 | Writer, reader, Material.
Mitch | 2024-09-30 | 16:00 | 2024-09-30 | 21:30 | 45565 | 45565 | 5.5 | 2 | 5.5 | Serialization.
Mitch | 2024-10-01 | 21:30 | 2024-10-02 | 0:40 | 45566 | 45567 | 3.1667 | 3 | 3.1667 | Serialization.
Mitch | 2024-10-02 | 19:00 | 2024-10-02 | 20:00 | 45567 | 45567 | 1 | 4 | 1 | Serialization.
Mitch | 2024-10-02 | 21:15 | 2024-10-03 | 0:20 | 45567 | 45568 | 3.0833 | 4 | 3.0833 | Serialization.
Mitch | 2024-10-03 | 21:00 | 2024-10-04 | 0:00 | 45568 | 45569 | 3 | 5 | 3 | Serialization.
Mitch | 2024-10-04 | 21:00 | 2024-10-05 | 1:55 | 45569 | 45570 | 4.9167 | 6 | 4.9167 | Scripting, serialization.
Mitch | 2024-10-07 | 21:00 | 2024-10-08 | 2:00 | 45572 | 45573 | 5 | 1 | 5 | Bug fixes.
Mitch | 2024-10-08 | 22:00 | 2024-10-09 | 0:45 | 45573 | 45574 | 2.75 | 2 | 2.75 | Bug fixes.
Mitch | 2024-10-10 | 4:00 | 2024-10-10 | 8:25 | 45575 | 45575 | 4.4167 | 1 | 4.4167 | Serialization, asset loading.
Mitch | 2024-10-10 | 21:00 | 2024-10-11 | 2:00 | 45575 | 45576 | 5 | 1 | 5 | Serialization, bug fixes.
Mitch | 2024-10-12 | 13:00 | 2024-10-12 | 15:55 | 45577 | 45577 | 2.9167 | 1 | 2.9167 | Rendering.
Mitch | 2024-10-12 | 20:00 | 2024-10-13 | 2:05 | 45577 | 45578 | 6.0833 | 1 | 6.0833 | Rendering.
Mitch | 2024-10-13 | 23:45 | 2024-10-14 | 2:15 | 45578 | 45579 | 2.5 | 2 | 2.5 | Rendering.
Mitch | 2024-10-14 | 18:00 | 2024-10-14 | 19:00 | 45579 | 45579 | 1 | 3 | 1 | Bug fixes.
Mitch | 2024-10-14 | 21:30 | 2024-10-14 | 23:40 | 45579 | 45579 | 2.1667 | 3 | 2.1667 | Bug fixes.
Mitch | 2024-10-19 | 23:00 | 2024-10-20 | 2:30 | 45584 | 45585 | 3.5 | 1 | 3.5 | Bug fixes.
Mitch | 2024-10-20 | 11:00 | 2024-10-20 | 15:00 | 45585 | 45585 | 4 | 2 | 4 | Bug fixes.
Mitch | 2024-10-20 | 21:00 | 2024-10-20 | 23:25 | 45585 | 45585 | 2.4167 | 2 | 2.4167 | Animations.
Mitch | 2024-10-21 | 22:00 | 2024-10-22 | 0:15 | 45586 | 45587 | 2.25 | 3 | 2.25 | Animations.
Mitch | 2024-10-22 | 20:00 | 2024-10-23 | 4:20 | 45587 | 45588 | 8.3333 | 4 | 8.3333 | Animations.
Mitch | 2024-10-23 | 20:00 | 2024-10-24 | 1:30 | 45588 | 45589 | 5.5 | 5 | 5.5 | Bug fixes.
Mitch | 2024-10-24 | 22:00 | 2024-10-25 | 2:05 | 45589 | 45590 | 4.0833 | 6 | 4.0833 | Audio.
Mitch | 2024-10-25 | 22:00 | 2024-10-26 | 1:00 | 45590 | 45591 | 3 | 7 | 3 | Input.
Mitch | 2024-10-26 | 11:00 | 2024-10-26 | 15:00 | 45591 | 45591 | 4 | 8 | 4 | Input, Sprites.
Mitch | 2024-10-27 | 21:00 | 2024-10-27 | 22:30 | 45592 | 45592 | 1.5 | 9 | 1.5 | Input.
Mitch | 2024-10-30 | 23:00 | 2024-10-31 | 1:00 | 45595 | 45596 | 2 | 1 | 2 | Building on new device.
Mitch | 2024-10-31 | 15:30 | 2024-10-31 | 19:00 | 45596 | 45596 | 3.5 | 2 | 3.5 | Building on new device.
Mitch | 2024-11-01 | 10:30 | 2024-11-01 | 11:30 | 45597 | 45597 | 1 | 3 | 1 | Bug fixes.
Mitch | 2024-11-06 | 19:00 | 2024-11-06 | 20:00 | 45602 | 45602 | 1 | 1 | 1 | Bug fixes.
Mitch | 2024-11-07 | 20:00 | 2024-11-08 | 2:15 | 45603 | 45604 | 6.25 | 2 | 6.25 | Sprite rendering.
Mitch | 2024-11-17 | 19:30 | 2024-11-17 | 20:00 | 45613 | 45613 | 0.5 | 1 | 0.5 | GUI.
Mitch | 2024-11-20 | 4:30 | 2024-11-20 | 8:30 | 45616 | 45616 | 4 | 1 | 4 | GUI, fix editor.
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Mitch |  |  |  |  | 0 | 0 | 0
Formulas:
Elapsed Hours Raw = (DAYS(Table1[[#This Row],[End Date]],Table1[[#This Row],[Start Date]]) + Table1[[#This Row],[End Time]] - Table1[[#This Row],[Start Time]]) * 24